## POA&M
PLAN OF ACTION & MILESTONES (POA&M)
System: Cybersecurity Homelab ¦ Owner: Gideon Sarfo-Nyantakyi ¦ Personal lab — public portfolio document ¦ Updated: September 30, 2026
System Name: | Cybersecurity Homelab (Kali Linux VM) | System Owner: | Gideon Sarfo-Nyantakyi | Date Prepared: | July 2, 2026 | Prepared By: | Gideon Sarfo-Nyantakyi | Scanner: | OpenVAS/GVM 26.17.0
POA&M Item # | Weakness Description | Source of Weakness | NIST SP 800-53 Control | Asset / System | Severity (CVSS) | Risk Level | Scheduled Completion | Milestone Changes | Milestone With Completion Date | Resources Required | Status | POC (Name) | Comments / Notes | Date Closed
POA&M-001 | No critical, high, medium, or low vulnerabilities detected on target host 10.0.2.15 during OpenVAS scan. Four (4) informational items filtered below QoD threshold of 70. | OpenVAS Vulnerability Scan Scan ID: cf296b45-e5a0-4735-80a3-1db0ddd48e45 Date: July 2, 2026 | RA-5 – Vulnerability Monitoring and Scanning | 10.0.2.15 (Kali Linux VM) OS: Linux Kernel CPE: cpe:/o:linux:kernel | 0.0 (Log) | LOW | N/A – No remediation required | No milestones required. System passed vulnerability assessment with zero actionable findings. | N/A | None – No remediation resources required | CLOSED – No Action Required | Gideon Sarfo-Nyantakyi | Clean scan result on freshly configured Kali Linux VM. Informational findings below QoD-70 threshold were reviewed and determined non-actionable. Next scan scheduled in 30 days per continuous monitoring plan. | July 2, 2026
POA&M-002 | Authenticated scanning not configured. Current scan used unauthenticated mode which may miss locally-exploitable vulnerabilities, missing patches, and software inventory details. | Scanner Configuration Review Date: July 2, 2026 | RA-5(5) – Vulnerability Monitoring and Scanning ¦ Privileged Access (authenticated scans) CA-7 – Continuous Monitoring | 10.0.2.15 (Kali Linux VM) | N/A | MEDIUM | October 31, 2026 (re-baselined; originally August 2, 2026) | Changed September 30, 2026: original milestones (July 15 – August 2, 2026) were missed. Re-baselined to October 31, 2026 to align with Lab 03. | Original (missed): M1 Research authenticated scan config – July 15, 2026; M2 Configure credentials – July 22, 2026; M3 Run authenticated scan – August 2, 2026 Revised: Configure SSH credentials in GVM, run authenticated scan, and document results – October 31, 2026 | OpenVAS/GVM documentation Kali Linux homelab environment | OPEN – Overdue, re-baselined | Gideon Sarfo-Nyantakyi | Authenticated scanning provides significantly more accurate results for patch status, software inventory, and local vulnerabilities. This is a standard ISSO practice for RMF-compliant assessments.
POA&M-003 | Scan scope limited to single VM (10.0.2.15) using VirtualBox NAT network. Real home network devices (router, endpoints) not included in current assessment scope. | Scan Scope Review Date: July 2, 2026 | RA-3 – Risk Assessment RA-5 – Vulnerability Monitoring and Scanning CM-8 – System Component Inventory | Homelab assessment scope (originally planned: home network 192.168.1.0/24) | N/A | LOW | August 16, 2026 | Changed September 29, 2026: approach changed from a bridged home-network scan to an isolated lab network (Lab 02), to avoid exposing an intentionally vulnerable VM and scanning devices outside sole authority. | Original: M1 Configure bridged networking – July 16, 2026; M2 Run network-wide scan – August 2, 2026; M3 Complete asset inventory – August 16, 2026 Actual: Isolated "GRC-Lab" network, target VM added, full scan and CM-8 inventory completed – September 29, 2026 | VirtualBox network configuration OpenVAS/GVM | CLOSED – Completed via Lab 02 | Gideon Sarfo-Nyantakyi | Closed by Lab 02 (02-Network-Enumeration): 4 components discovered and inventoried, 30 services enumerated on the target, findings tracked as POA&M-004 to POA&M-012. | September 29, 2026

## Summary Dashboard
POA&M SUMMARY DASHBOARD
System: Cybersecurity Homelab ¦ Scan Date: July 2, 2026 ¦ Scanner: OpenVAS GVM 26.17.0 ¦ Updated: September 30, 2026
METRIC | VALUE | STATUS | NOTES
Total POA&M Items | 3 | — | All items documented
Critical Findings | 0 | PASS | Zero critical vulnerabilities
High Findings | 0 | PASS | Zero high vulnerabilities
Medium Findings | 0 | PASS | Zero medium vulnerabilities
Low Findings | 0 | PASS | Zero low vulnerabilities
Informational (Log) | 4 | REVIEWED | Below QoD-70 threshold, non-actionable
Open Items | 1 | IN PROGRESS | POA&M-002 (overdue; re-baselined to October 31, 2026)
Closed Items | 2 | CLOSED | POA&M-001, POA&M-003
Scan Coverage | 1 Host | EXPANDED | Scope expanded in Lab 02 (isolated network, 4 components); POA&M-003 closed
Scan Type | Unauthenticated | PLANNED UPGRADE | Authenticated scan planned per POA&M-002
Next Scan Date | August 2, 2026 | MISSED | Follow-up scan did not occur; to be performed after Lab 03
NIST Controls Addressed | RA-5, RA-5(5), CA-7, RA-3, CM-8 | — | Mapped in POA&M sheet